# ENGR90037 – 2026 Semester 2, Assignment 2 – Project Retrospective

Bagus & Yimin, September 2026

## Capstone Project Retrospective

You are the project manager of your capstone project. Early in the project you submitted a Project Charter setting out your objective and scope, risks, milestones and success measures.

The project is now at its midpoint. Your organisation requires every project to run a retrospective at this stage: a structured look back at how the project has actually run against the plan, while the second half can still benefit from what you find. Your sponsor has asked you to facilitate the retrospective with your team and write up the outcome. No specific format is required.

A retrospective is not a status update. Your sponsor can already see where the project stands. What they want to know is how you, as project manager, have monitored and managed the project against the plan: what changed, why, what you did about it, and what you now know that you did not at the charter stage.

## PART 1: Written Statement

## Submission date for part 1: 11:59 PM on Friday of week 11

Length: maximum 850 words

This is the required word count of the submission, including any footnotes you may choose to include. It does not include the bibliography or section headings

Submission: Project retrospective is to be submitted electronically via Canvas using the Turnitin link therein.

## Academic Honesty and Plagiarism:

Students are encouraged to review the following website: https://academicintegrity.unimelb.edu.au/

Project Retrospective:

In writing this project retrospective you must provide updates on these FOUR general aspects:

- Did you change or update the project objective and scope in the last half semester? How was this raised, and how did you draft the updated objective and scope?

- You identified several major risks and their treatments (countermeasures) in the submitted Project Charter. Now that the project is at its midpoint, have any of those risks occurred, and how effective were the countermeasures? Were there any unforeseen risks that surprised you, and what did you do?

- Provide updated milestones and an updated Gantt chart. Describe your progress at the date you are writing this report. Are you ahead of or behind schedule? What are the effects on the critical path and on the major milestones? How different is your current Gant chart and from your charter five-six weeks ago?

- People management and teamwork are crucial in delivering projects. How has your project team performed, and how have you performed yourself? How will you keep your project team motivated?

In addition of those four aspects above, you must consider TWO OTHER components of what your sponsor is looking for. Some examples of these components are below:

- Critical factors.

- Performance measurement criteria

- Stakeholders

- Financial

- Sustainability

The four required aspects set out the kind of thinking we are looking for, and the same approach applies to whichever two you choose from above. Start from what you set out in the Charter: has it changed, how, why, and what did you do about it?

Each Capstone projects would have different specific requirements, some projects may have budget/financial requirement, some do not. Some may have potential sustainability components, and some do not. Some industry projects may require you to have specific performance measurement criteria while other do not. Hence you just need to choose two components from the five listed above.

## Writing tips

- Assume your sponsor is unfamiliar with your field of engineering, so avoid technical terminology where you can.

- The project retrospective is not simply a description of status — not just an updated version of the objective, the milestones and the Gantt chart. What your sponsor is looking for is how you, acting as project manager, continuously monitor and manage your capstone project against the plan.

- Refer back to your lecture slides as a reference in addressing the questions.

PART 2: Q&A

Oral presentation during week 12

You submitted your retrospective yesterday. Today your sponsor has 15 minutes. They will read the write-up over the weekend, but first they want to hear the lessons from you directly.

A briefing is very different from a written retrospective. Think about what you should focus on. Should you spend it on what went as planned and on re-telling what the plan was, or should you focus on the progress, on what went wrong and on what surprised you and your team? Also, what has been the most challenging part so far, and how did you and your teammates handle it? Close with one or two lessons learned. State each as a lesson and the action you are taking as a result. A lesson without an action is just an observation.

Here is the format you can consider for designing your presentation slides: half a slide to one slide for project background and context. One to two slides for the project retrospective. Maximum two slides are allowed in the oral presentation. The power point presentation duration is maximum 5-minutes.

Expect 10  minutes of Q&A. Your sponsor may ask follow-up questions about the project.

You will be required to submit your slides electronically via Canvas after your presentation using the Turnitin link as reference.

## Capstone Project Retrospective – general information

Total available marks = 15

# Marking Criteria

In marking your project retrospective, three basic criteria are relevant to your mark.

- How well you describe the project management practices, especially when things do not go as planned, and what you have learned from them.

- How well you understand the relevant project management concepts and frameworks.

- Whether your presentation, both written and verbal, is clear and professional.

### AI Usage rule

Please refer to the Faculty and Capstone AI rules (see Canvas). All AI usage needs to be stated clearly in the report and slides.

# Referencing

Referencing is a requirement for this assessment task and includes acknowledging all and any use of artificial intelligence. Please review the University of Melbourne policy of the use of artificial intelligence (also refer to the Faculty and Capstone AI rules in Canvas).

The following website contains information and advice regarding referencing and citation rules, as well as links to further useful guidelines/resources:

https://students.unimelb.edu.au/academic-skills/resources/referencing/referencing-essentials