Project Charter - Towards a Robotic and AI-Enabled Autonomous Chemical Laboratory.

| Document information | Details |
| --- | --- |
| Team code | M-21-EJON-009 |
| Authors | Yifan Wu; Xinkai Zhang |
| Document issued | 27 Aug 2026 |
| Version | 0.2 - Revised scope draft |

1. Objective

To deliver and experimentally evaluate a staged proof-of-concept robotic system that integrates a commercial robot arm, the inherited custom gripper, a mobile base, perception, motion planning, task-level control and safety supervision. In a controlled representative laboratory workcell, the system will transport a non-hazardous surrogate test tube from a defined source workstation to a measured representative instrument fixture, open the lid, insert the tube, close the lid and actuate the start button. Stages 1 to 3 will progress from simulation to proportionate hardware validation in the Human Robotics Lab (Building 170, Room E110); Stage 4 human-movement and dynamic-obstacle scenarios will be evaluated in simulation only. Simulation will be retained as a regression environment throughout the project.

2. Scope

2.1 Must Have

- A modular simulation model and software architecture for the robot arm, inherited gripper, mobile base, laboratory workstations and safety supervisor.

- Stage 1: simulated and hardware-validated fixed-arm test-tube pick, transfer from point A to point B, release and safe return.

- Stage 2: simulated and hardware-validated fixed-arm workflow comprising test-tube pickup, lid opening, tube insertion, lid closure and start-button actuation in a controlled representative workcell, with each skill validated individually before the integrated sequence.

- Stage 3: simulated and hardware-validated integration of the mobile base, arm and gripper in the Human Robotics Lab, comprising navigation between representative workstations, a safe arm transport state, workstation-relative localisation and the complete instrument sequence.

- Stage 4: simulation-only dynamic-obstacle and human-movement scenarios that apply defined navigation, slowdown, protective-stop, timeout and recovery responses while preserving task state.

- An explicit task state machine with bounded retries, failure reporting and safe abort behaviour for grasp, localisation, motion, insertion, lid and button failures.

- A documented safety architecture covering operating modes, collision models, restricted zones, protective stopping, hardware emergency-stop boundaries and restart conditions.

- Repeatable functional and performance testing with recorded conditions, sample counts, units and uncertainty or dispersion.

2.2 Should Have

- Workstation-relative perception that compensates for residual mobile-base and object-pose error.

- A measured representative instrument fixture that reproduces the lid, insertion opening and start-button geometry without requiring the mobile system to enter the active chemistry laboratory.

- Terminal visual, force or compliant correction for contact-rich skills where measured tolerances show that open-loop motion is insufficient.

- Automatic confirmation of test-tube placement, lid state or button actuation in the representative workcell.

2.3 Could Have

- A dedicated lid-opening or button-actuation tool.

- Higher-fidelity compliant contact and filled-test-tube models.

- Learning-based perception or residual correction for a demonstrated limitation of the deterministic baseline.

- Integration with laboratory data systems or a real instrument after separate access and safety approval.

- A limited Stage 3 pilot deployment of the integrated mobile platform in the chemistry laboratory, only after route and clearance measurements, instrument-protection planning, scheduled access and separate safety approval.

2.4 Won't Have

- General operation of arbitrary laboratory instruments, lids, buttons or labware.

- Autonomous scientific hypothesis generation or chemistry optimisation.

- Handling hazardous, reactive, infectious, pressurised or temperature-sensitive materials.

- Real-person dynamic-obstacle or collaborative-robot hardware testing; Stage 4 is simulation only.

- Formal machinery, functional-safety or collaborative-robot certification.

- Unrestricted laboratory navigation, multi-robot coordination or continuous production operation.

3. Cost - Budgetary Estimate

Existing university-owned equipment will be recorded as in-kind access rather than new project expenditure unless the subject coordinator requires its replacement value to be included.

3.1 Equipment Costs

| Item | Basis | Budgetary estimate (AUD) |
| --- | --- | --- |
| Delivered commercial robot arm | University-provided, already delivered | $0 direct project expenditure |
| Inherited custom gripper and existing CAD | University-provided inherited asset | $0 direct project expenditure |
| Mobile base and representative instrument fixture | University/partner assets; active chemistry-lab deployment is not assumed | [TO CONFIRM] |
| Sensors, mounting hardware and fabricated parts | Only if required after measurement | [TO CONFIRM] |
| Sundries | Test tubes, surrogate fixtures, fasteners, wiring and printing | [TO CONFIRM] |

3.2 Personnel Costs

| Resource | Calculation | Estimated cost (AUD) |
| --- | --- | --- |
| Student team | [number of students] x [hours per student] x $100/h | [TO CONFIRM] |
| Supervisor | [supervisor hours] x $200/h | [TO CONFIRM] |
| External adviser(s) | [adviser hours] x $200/h | [TO CONFIRM] |

3.3 Total Estimated Cost

Total budgetary estimate: [TO CONFIRM after personnel hours and equipment budget are agreed]

4. Stakeholders

| Stakeholder | Name/organisation | Role |
| --- | --- | --- |
| Supervisor | Jonathan Eden | Provide academic guidance, review progress and approve changes to project scope. |
| Chemistry adviser/customer | Greg Qiao | Define the laboratory workflow, provide instrument expertise and accept task requirements. |
| Mobile-base partner team | [TO CONFIRM] | Provide the mobile-base mechanical, electrical, software and safety interfaces. |
| Laboratory management/safety representative | Jonathan Eden / Human Robotics Lab | Control access to Building 170 Room E110 and approve the conditions for controlled hardware testing. |
| Project team | Yifan Wu; Xinkai Zhang [student IDs TO CONFIRM] | Manage the project; design, implement, test and document the deliverables. |

5. Timing of Major Milestones

Dates below are a first planning draft and must be aligned with the official subject calendar before submission.

| Milestone | Target date | Acceptance evidence |
| --- | --- | --- |
| Project Charter and scope approved | 4 Sep 2026 | Supervisor and chemistry stakeholder review recorded |
| Delivered arm commissioned and task hardware measured | 18 Sep 2026 | Model/controller identity, basic motion, safety state, TCP inputs and instrument measurements recorded |
| Stage 1 simulation and fixed-arm hardware baseline completed | 2 Oct 2026 | Repeatable A-to-B pick, transfer and release tests completed |
| Stage 2 instrument skills validated individually in simulation | 23 Oct 2026 | Open-lid, insert, close-lid and button skills each pass defined tests |
| Stage 2 integrated fixed-arm workflow demonstrated | 6 Nov 2026 | Complete simulated and controlled-workcell hardware sequence using a non-hazardous surrogate |
| Mobile-base interface and preliminary system safety architecture frozen | 18 Dec 2026 | Interface control document and hazard/control review |
| Stage 3 controlled-lab mobile integration completed | 19 Mar 2027 | Simulation and Human Robotics Lab hardware evidence for navigation, safe transport, relocalisation and the representative instrument workflow |
| Stage 4 simulation-only dynamic-obstacle evaluation completed | 16 Apr 2027 | Avoid/slow/stop/timeout/recovery scenarios evaluated with simulated moving people and obstacles |
| Final controlled-workcell validation completed | 14 May 2027 | Functional, performance and fault-injection results recorded; no active chemistry-lab deployment required |
| Final report and presentation | [TO CONFIRM] | Submitted by official subject deadlines |

6. Success Measurement Criteria

6.1 Functional Tests

- Stage 1 completes test-tube pickup, verified grasp, A-to-B transport, release and safe return in simulation and on the fixed-arm hardware baseline.

- Stage 2 completes lid opening, tube insertion, lid closure and button actuation in simulation and on the fixed-arm controlled-workcell hardware baseline; each skill also fails safely when its preconditions are not met.

- Stage 3 integrates the mobile base, arm and gripper in simulation and in the Human Robotics Lab, navigates between representative workstations, uses a safe arm transport state, relocalises and executes the representative instrument sequence.

- Stage 4 applies the specified avoid, slow, stop, timeout or recovery response when a simulated moving person or dynamic obstacle enters each defined zone; no real-person hardware test is required.

- Injected grasp, localisation, planning, insertion and communication failures terminate in the specified safe state without unlimited retrying.

6.2 Performance Tests

| Measure | Provisional minimum success criterion |
| --- | --- |
| Stage 1 complete cycles | At least 90% success over N >= 20 trials under stated test conditions |
| Stage 2 complete workflows | At least 80% success over N >= 10 controlled hardware trials, supported by a larger simulated regression set; each unsuccessful skill classified |
| Stage 3 complete workflows | At least 80% success over N >= 10 controlled Human Robotics Lab hardware trials with stated navigation perturbations, supported by simulation |
| Dynamic-obstacle scenarios | No collision in the defined simulation test set and the specified response is triggered in every scenario |
| Grasp, docking, insertion and placement error | [TO CONFIRM after physical geometry, tolerance and uncertainty measurements] |
| Stage 4 safety response and separation | Defined and evaluated in simulation only; no human-shared hardware safety or certification claim |

7. Critical Factors

| Critical input/action | Delivered by | Required by |
| --- | --- | --- |
| Approval of the objective, MoSCoW scope and representative instrument workflow | Jonathan Eden and chemistry adviser | 4 Sep 2026 |
| Confirmed robot-arm model, controller, safety interface and Human Robotics Lab access | Jonathan Eden / Human Robotics Lab | 11 Sep 2026 |
| Access to the target test tube, instrument, lid and button for measurement | Chemistry stakeholder | 11 Sep 2026 |
| Inherited gripper hardware, firmware, wiring and available raw data | Previous team/project custodian | 18 Sep 2026 |
| Mobile-base interface, payload/stability evidence and integration schedule | Mobile-base partner team | 30 Oct 2026 |
| Approval of controlled hardware test conditions in Building 170 Room E110 | Jonathan Eden / laboratory management | Before each hardware stage |

8. Major Risks and Treatments

| Major risk | Potential effect | Treatment/countermeasure |
| --- | --- | --- |
| The inherited gripper performs differently from the report, CAD or rigid-contact simulation. | Stage 1 grasping or release may fail and invalidate later stages. | Front-load inspection and calibration; retain replaceable pads/fixtures; update the model after each hardware test. |
| The mobile base is late or incompatible with the arm payload, power, mounting, network or safety interfaces. | Stage 3 hardware integration may be delayed or reduced. | Freeze an interface control document early; use simulation and a fixed-base fallback; escalate unmet interface dates. |
| Measured lid, insertion or button requirements exceed the capability of the current gripper and open-loop arm control. | The complete instrument workflow may not be achievable with the inherited end effector. | Measure early; test skills independently; use compliant/visual correction, a guide or a dedicated tool if justified. |
| Simulation assumptions produce unacceptable real-world pose, contact or timing errors. | Simulated success may not transfer to hardware. | Use stage-by-stage Sim2Real validation, maintain regression tests and record every material difference in the Sim2Real log. |
| The available Human Robotics Lab test area cannot provide the required exclusion zone or clear mobile route. | Stage 3 hardware integration may be delayed or restricted. | Survey and mark the route early; schedule exclusive test windows; keep emergency egress clear; reduce the hardware scenario while retaining full simulation evidence. |
| The arm and mobile base do not provide a verified coordinated hardware stop path. | Integrated mobile hardware testing cannot proceed under the proposed controls. | Verify each hardware emergency-stop boundary before integration; define operating modes and restart conditions; retain simulation and isolated subsystem tests if coordinated stopping cannot be accepted. |

8.1 Overall Probability of Technical Success

The overall probability of technical success is estimated at 80%. The fixed-arm and simulation components use established robotics methods, a delivered commercial robot arm is available, and required hardware work is limited to a controlled representative workcell. The complete proof of concept still depends on inherited-gripper performance, mobile-base integration, precision contact with the representative instrument fixture, Sim2Real correction and verified hardware stop boundaries. Treating active chemistry-lab deployment as a Could Have and excluding real-person dynamic-obstacle hardware testing from the success condition reduces uncontrolled environmental and safety dependencies while preserving the project's integration objective.

9. Signatures

Team members may sign this draft after the content and budget are agreed. Supervisor and external adviser signatures can be collected after assessment feedback if required.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Team member | Yifan Wu |  |  |
| Team member | Xinkai Zhang |  |  |
| Supervisor | Jonathan Eden |  |  |
| Chemistry adviser/sponsor | Greg Qiao |  |  |

10. References

- Warfield, B. (2026). Skeleton Project Charter and ENGR90037 lecture materials. University of Melbourne LMS.

- Le, N. B. N., Fong, K. H., Poon, S. Y., & Wang, S. (2026). Implementation of a Robotic Hand for Lab Experiments. University of Melbourne Capstone report, 29 May 2026.

- Yoshikawa, N. et al. (2022). Chemistry Lab Automation via Constrained Task and Motion Planning. arXiv:2212.09672. https://doi.org/10.48550/arXiv.2212.09672

- Burger, B. et al. (2020). A mobile robotic chemist. Nature, 583, 237-241. https://doi.org/10.1038/s41586-020-2442-2

- Angelopoulos, A., Verber, M., McKinney, C., Cahoon, J., & Alterovitz, R. (2023). High-Accuracy Injection Using a Mobile Manipulation Robot for Chemistry Lab Automation. IEEE/RSJ IROS. https://doi.org/10.1109/IROS55552.2023.10341743

- [TO CONFIRM: official Project Brief and supervisor/chemistry stakeholder meeting record].

11. Use of AI Tools

OpenAI ChatGPT/Codex was used to generate and structure an initial draft from project information supplied by the team, and to review clarity and consistency between the objective, scope, milestones, success criteria and risks. All technical claims, scope decisions, cost assumptions and final wording will be checked and approved by the project team before submission; the team retains full responsibility for the submitted document.