### FINAL DRAFT (Prior to Sign-off by Supervisor)

# Project Charter – Title of Your Project and Team Code

Authors	Names and ID numbers of all team members Document Issued on	Date of submission – just one submission per team Document Version No.	1.0 (or 1.1 or whatever)

Original template prepared Bob Warfield, February, 2026

### NOTES:

- Engineers Australia, as a condition for accrediting this ME course, require that all graduating engineers will have a foundation in Project Management. Therefore, for the purposes of this assignment, we assume that the students will manage their own Capstone Project as well as producing the deliverables. However, in some cases the project may actually be managed by the Supervisor instead. If that is the case, then the students need to complete this assignment as if they were in the role of Project Manager, but they may need to adjust those roles for their actual project work.

- This Skeleton Charter is provided as the foundation of your report to senior management. It must be brief and to the point, and easily understood by a senior manager – someone like the Dean of the Melbourne School of Engineering or other senior stakeholders.

- Text in red is meant for your guidance only. Replace all the text in red with your own project-specific information. For example, replace *Supervisor’s Name* with the actual name, such as “Dr. Jane Doe”.

- Ensure that all red text is replaced or deleted before final submission. Double-check to confirm no red text remains. It is amazing that this instruction is needed.

- Since you may use AI tools, a high standard of professional reporting is required. Marks will be deducted for errors of spelling or grammar, or for lack of clarity and conciseness. All abbreviations should be spelled out on first occurrence. Page breaks should be managed thoughtfully. For example, you should NOT have five milestones at the bottom of one page and another one at the top of the next page, otherwise the marker or senior manager might miss the last one.

- IMPORTANT:

You may use AI tools to assist you, including AILA, which is available through LMS.

However, to avoid questions about originality and collaboration, you must indicate how you made use of AI TOOLS. There is a Section at the end of this document where you can do that.

S.M.A.R.T.

The concept of “S.M.A.R.T” is discussed in lectures. In summary, it means: S – Specific.

Examples of terms that are NOT specific include: “understanding”, “user-friendly”, “well-documented”, “ongoing research”.

M – Measurable.

Items should be measurable either objectively or subjectively. If they are subjectively measured, there should be some indication of how the assessment will be done. For example “achieve 80% or better approval in a user survey”.

A – Achievable.

Items should not be so optimistic as to be unachievable. An example of an unachievable aim would be, “100% reliability.” This would imply that the thing referred to will never fail.

R – Relevant.

All items should be relevant to the project. T – Time Framed.

In the case of the Project Objective, it is taken for granted that the time frame is the duration of the Capstone Subject. This does not need to be explicitly stated. Milestones and Critical Factors need a stated Time.

The verbs used in the objective should emphasize delivery, not activities. Poor choices that should NOT be used are:

- Investigate

- Research

- Look into

- Study

- Understand

- Read

- Discuss

While those are worthwhile activities, the words do not give any indication that there is an end goal or a specific time to finish. If something is to be “discussed” that could be achieved in one minute in the local coffee shop with no clear outcome. Or it could continue for months. There is no clear objective of “discussing” something and there is no concept of bringing it to completion.

Better verbs to include in your Charter include, for example:

- Build

- Describe

- Explain

- Document

- Decide

- Determine

- Deliver

Those verbs emphasize what is to be delivered, and they give a sense that the work will be completed at some time. Once something is built, it is built – work is completed. Compare the

verb “discuss” with the verb “decide”. Often a decision is reached through discussion, but some discussions may not lead to any decision.

# Objective

What are you planning to achieve and deliver? The answer to this question is the Objective – the most important part of the Charter. The reader is interested in deliverables, not your activities.

Apply the concept of S.M.A.R.T.

Having read and understood the Brief Description of your Final Year Project, and having discussed the project with your Supervisor (and Adviser), express the Objective of Your Project in your own words in a way that your senior manager will understand. For example, if you were creating an alarm clock, you might say something like:

- To produce and test a prototype of a “Waker-Upper” device that will wake the user at a pre-set time, and also display the time of day. The prototype is to be used as a Proof of Concept for a potential mass-market product, which could be called an “Alarm Clock”.

# Scope

See lecture material on MoSCoW Method. Some projects may not have items in every one of the categories.

Everything in the “Must” or “Should” categories must be NECESSARY to achieving the objective as stated. Taken together, all the items in the “Must” and “Should” categories should be SUFFICIENT to achieve the objective. Do not introduce any items in the “Must” or “Should” categories that are beyond the stated scope.

“Could” items might be included in this project, or in a future project.

Items mentioned in the “Won’t” category help to manage the expectations of the reader.

Must Have:

- Necessary features / performance

Should Have:

- Desirable features / performance

Could Have:

- Optional features / performance

Won't Have:

- Explain what is NOT included, even though it might be expected by some readers. Example: Market Research

# Cost – Budgetary Estimate

This is the second most important item in your Charter, after the Objective.

“Budgetary Estimate” means the estimated maximum you may spend before asking for permission to go over-budget. It does not require your estimate to the nearest dollar and cent.

The cost per hour is not the salary you are paid, it is the hypothetical total cost of employment (typically about double the salary). Student hours should be costed at $100 and supervisor / adviser hours at $200.

All equipment costs (hardware or software) that are worth less than $100 each should be bundled up into a one-line entry called “Sundries” (maybe two lines if the total goes over $1000)

Check for numerical errors. Errors in calculation indicate a superficial approach to managing the project. This may seem OK for a student exercise, but it is not a good look for a professional engineer. Example follows:

## Equipment Costs

EXAMPLE: Nil

## Personnel Costs

EXAMPLE: Student Hours: 720 hours (360 hours × 2 students) at $100 per hour	$72,000 EXAMPLE: Supervisor Hours: 48 hours at $200 per hour		$9,600

## Total Estimated Cost

EXAMPLE: Total	:81,C00

# Stakeholders

For each stakeholder, give their name (include title and position if relevant), and their role in this project.

## Supervisor:

Stakeholder: Title (Prof., Assoc. Prof., Lecturer, . . .), Name, Department

Role: Provide academic guidance, oversee project progress, and ensure alignment with departmental goals.

## External Adviser:

Stakeholder: Position, Name, Department and/or Company

Role: Offer expertise relating to best practice. Approve scope.

## Team Members:

Stakeholder: Repeat your names and IDs here.

Role: Manage the project, and produce project deliverables.

# Timing of Major Milestones

All milestones should be S.M.A.R.T. as described above.

Remember benefits of front loading – bring forward the most challenging elements of the project. If appropriate, prototype aspects of the hardware, software, and analysis methods.

For Milestones, where possible, a precise date should be given. If that cannot be done, it is OK to have some leeway in the time specified – up to about a week. For example, the time might be stipulated as “the final week of Semester 1”, or “the first week of September”.

Example Milestones:

| 1. Determine the study scope and case study | 17/03/2023 |
| --- | --- |
| 2. Initial explanatory analysis completed | 24/03/2023 |
| 3. Draft report completed | 22/09/2023 |
| 4. Final Report Submitted | 20/10/2023 |
| - Presentation (Oral Exam) given during the examination period - Success Measurement Criteria | 30/10/2023 |

When you are finished, what will you MEASURE or DEMONSTRATE to PROVE that your project was a success, beyond any possible dispute? You should include two types of test: functional and performance.

## Functional Test

Does the project deliverable perform the functions planned?

Apply the concept of S.M.A.R.T. The time frame does not need to be specified in this section since it is defined elsewhere.

Don’t use phrases like “user-friendly interface” or “full documentation” which are not sufficiently specific. Instead, stipulate a usability test for the interface, or give a list of documentation to be included.

Example:

    - The “Waker-Upper” displays the time of day.

    - The alarm on the “Waker-Upper” sounds at a pre-set time.

## Performance Test

How well does it perform? Include quantitative targets if possible.

Don’t use phrases like “no errors” or “completely reliable” as these are not realistic. Instead, be more modest and allow for the WORST performance that would still be considered SUCCESSFUL.

Remember that “Ǫuality” is defined as

### “What customers get out of your product, and are willing to pay for.”

For example:

    - The time on the “Waker-Upper” should be accurate to within 2 minutes per day, or better. This indicates that you consider better accuracy would not be rewarded sufficiently by the willingness of customers to pay more for the product.

# Critical Factors

Critical Factors (sometimes called “Critical Success Factors” or CSF) are important things you need to GET and also VERIFY that you GOT them. CSF should be S.M.A.R.T.

A CSF is something that must be GIVEN to the project in good TIME, otherwise the project will be put in jeopardy.

When the CSF is obtained, the Project Manager should be able to say, “Yes, it has now been received.” CSFs do not include your routine processes which are under your control. CSFs include only specific critical

INPUTS or ACTIONS that are generally outside your direct control, but must arrive in good time, or the project is

doomed.

Each CSF should include what is to be given to the project, who should give it, and when it is needed. Possible examples:

Factor: Approval of Proposed Design

Delivered by: Supervisor

Date: 1 September 2025

Factor: Permission for Site Visit Delivered by: External Adviser Date: End of Semester 1, 2025

Routine requirements and things that are directly under the control of the Project Manager should NOT be included here. Examples of UNACCEPTABLE Critical Factors are:

- Weekly (or frequent, or bi-weekly) meetings with supervisor. Your project will not be put into jeopardy if the supervisor misses one or two meetings.

- Good teamwork – this is not S.M.A.R.T. It is expected to happen without any specific input, and is too vague to state: “Yes, it has been received now.”

- A Project Plan – this is under the control of the Project Manager, and is routinely expected.

Critical Factors and Risks are related. Critical Factors are things you hope to get, and will cause a problem if you don’t get them. Risks (of the negative sort) are things you hope will not happen, and if they do happen you will need to apply your management abilities.

# Major Risks and Treatments (Countermeasures)

## Risks

This is separate from your General Risk Assessment (GRA), and it fulfils a different purpose. The purpose of this section of the Charter is to summarize risks that affect the probability of project success – finishing on time, on budget, up to expected quality.

Risks are RANDOM future events which, IF they occur, can affect the outcome of the project. Technically, risks can have beneficial or detrimental effects. In this context almost all risks will have detrimental effect. Every Risk must have a commensurate Countermeasure (or Treatment). For example, if a risk is “not getting something” consider whether that specific “something” could be treated as a Critical Factor instead.

Risks are NOT issues which are KNOWN TO APPLY – any such issues should be dealt with in one or more tasks. Risks are NOT factors under the control of Project Management or Team Members. For example, “poor motivation”, or “general confusion about objectives” are issues rather than risks.

This section is for “Major Risks”. These include risks that you need to discuss with your Sponsors. You should NOT include minor, routine, mundane, or generic risks. If a risk has a known solution that is generally available, it should NOT be included unless that is necessary to remove any doubt. Examples of risks that usually should NOT be included are: “risk of burns while soldering”, “risk of electric shock while working on systems using commercial AC”.

Do not include a generic people risk of the form: “risk of some members not completing their work on time”. If there is a specific, named person whose contribution is essential, the absence or lateness of that individual may be included as a Major Risk. State why that individual is essential, and give your countermeasure.

## Overall Probability of Technical Success

A numerical estimate (best guess) is expected, along with a brief explanation. As a general guideline, here are some possible suggestions, depending on the type of project:

- Exploration of technological options - Research prior to Development.	Less than 60%

- Investigation of possible new technology - Bleeding Edge.	60% -75%

- Development based on untested technology - Proof of Concept.	75% - 90%

- Technology is well known, but not familiar to Project Team.	90% - 95%

- Improvement of existing product - Refinement Project.	95% - 99%

This Section refers to Technical Success – do not include Probability of Commercial Success. Note that in a real-world development project the Probability of Commercial Success would also be assessed, assuming that the project will achieve Technical Success.

# G. Signatures

YOU DO NOT NEED your Supervisors’ or Adviser’s signatures to submit this Charter for assessment. Just sign it yourself, and leave space for the other signatures which you will collect later. Remember that this Charter assume YOU are the Project Manager. Also, you may need to adjust the Project Charter after you get feedback for this assignment.

| Team Members |  |  |
| --- | --- | --- |
| Name: | Signature: | Date: |
| Name: | Signature: | Date: |

| Supervisor Name: supervisor name | Signature: | Date: |
| --- | --- | --- |
| External Sponsor Name: sponsor /adviser | Signature: | Date: |

# References

University of Melbourne sources do not need full details of how to find them. For example:

  - Warfield, Bob (2025) Skeleton Charter and Lecture Materials, LMS

  - {Supervisor, Title} (2025) Brief Project Description

For sources OUTSIDE the University of Melbourne, please include a URL or DOI wherever possible. For example:

  - Baillifard, A., Gabella, M., Lavenex, P., C Martarelli, C. (2023). Implementing Learning Principles with a Personal AI Tutor: A Case Study. ArXiv, abs/2309.13060. https://doi.org/10.48550/arXiv.2309.13060

# Use of AI Tools

Use of AI tools as assistants or research is allowed provided you state which ones you used and how. This will help to clarify the originality of your work and any question of collaboration.

Do not rely on AI to do the job for you (or ask it to write an entire report), and remember you retain accountability for everything that you submit. If AI makes a mistake and you submit it, it becomes YOUR mistake.

Give a brief summary of which tools you used and how. Examples:

  - AILA “Project Planning Workbench” – as a tutor

  - Consensus and Perplexity – assistance with literature search

  - Claude – to help with expression

  - ChatGPT – final edit

You have accountability for ensuring privacy of sensitive information. The AILA tool is run locally and presents minimal risk. Other tools have varying policies regarding use of user data for training and other aspects of privacy. It is up to you to make sure that the confidentiality of the information in your work is respected.

NOTE: You need to be extra careful in using AI if you are working in an Industry Based Project because some will involves Non-Disclosure-Agreement. Uploading classified information into an open AI system such as Gemini or Chat GPT will result in the information being released to the internet. This may have legal repercussion.

Ǫuestions?

Post general questions about the assignment or the lectures (anonymously if you wish) to the ED Discussion Board, Dr Bagus Nugroho will endeavor to answer.

If he has not answered for more than three days, please email him at bagus.nugroho@unimelb.edu.au as ED sometimes quite late in providing warning to instructors.

If you have a question of a personal or private nature, email Dr Bagus Nugroho , if he is unable to provide answer, he will refer to Dr Yimin Li

If you email Dr Nugroho a general question, rather than a private one,  will transfer it to the Discussion Board before answering it. This will just result in unnecessary delay.